## Users
id | name | email | phone | role | plant | dept | superior | initials | color | username | password | "
U01 | Prashant | singhprashant7972@gmail.com | 7049091928 | Hod | All | Management | " | PR | #272262 | Prash | 1401 | "
U02 | Manish Manjhi | manish.manjhi@groupsignet.com | 9599193574 | HOD | Signet | Business Excellence | " | MM | #272262 | Manish | 1975 | "
U03 | Mohit Patsariya | mohit.patsariya@adroitindustries.com | +91 883 973 8487 | Supervisor | Adroit1 | Business Excellence | Manish Manjhi | MP | #E69903 | Mohit | 123

## Reasons
id | reason | category
R001 | Machine breakdown / failure | Equipment
R002 | Quality defect observed | Quality
R003 | Safety hazard identified | Safety
R004 | Process deviation found | Process
R005 | Customer complaint follow-up | Customer
R006 | Preventive maintenance due | Maintenance
R007 | Material shortage / delay | Supply Chain
R008 | Operator error / training gap | People
R009 | Tool / die wear or damage | Equipment
R010 | Energy / utility issue | Utilities
R011 | Compliance / audit finding | Compliance
R012 | Yield loss / rework identified | Quality
R013 | New project / improvement initiative | Projects
R014 | Management directive | Management
R015 | Repeat issue — root cause pending | Quality

## EscalationMatrix
id | daysOverdue | level | target | action

## Permissions
id | canAddAction | canEditAction | canDeleteAction | canCreateMeeting | canCreateProject | canViewDashboard | canManageUsers | canExport

## MeetingPresets
type | attendees | instructions

## Audit
id | ts | sn | text | level | target | reason

## Plants
name | location | head
Adroit1 | Pithampur | Manish Manjhi
Signet | Pithampur | Manish Manjhi
All | Both | Admin

## Departments
name | head | id
PE | A | d-0
RPVC | B | d-1
PVC | C | d-2
Drip | D | d-3
Business Excellence | Manish Manjhi | D5

## Actions
id | sn | src | section | plant | dateOfAction | text | responsible | allocatedBy | due | status | remarks | priority | revisions | revisionHistory | created | closedOn | project | messages | pendingConfirmation | """""""""""""""""""""""""""""""" | """"""""""""""""""""""""""""""" | """""""""""""""""""""""""""""" | """"""""""""""""""""""""""""" | """""""""""""""""""""""""""" | """"""""""""""""""""""""""" | reasonOfAction | machineName
1777128240079 | ACT-018 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Tank Cap trail to be done | Manish Manjhi | Manish Manjhi | 2026-04-28 | COMPLETED | Done | NORMAL | 1 | [{"date":"2026-04-27","from":"2026-04-27","to":"2026-04-28","by":"Manish Manjhi"}] | 2026-04-25 | 2026-04-27 | Mr. Saurabh Signet Work | [{"id":1777270814135,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish has marked this action as complete and sent it for confirmation by Manish.","ts":"2026-04-27T06:20:14.135Z"},{"id":1777270815715,"author":"System","authorInitials":"SYS","authorColor":"#C0392B","text":"Manish has rejected the completion and reopened this action.","ts":"2026-04-27T06:20:15.715Z"},{"id":1777272201565,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish has marked this action as complete and sent it for confirmation by Manish.","ts":"2026-04-27T06:43:21.565Z"},{"id":1777272202741,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T06:43:22.741Z"},{"id":1777278746541,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T08:32:26.541Z"},{"id":1777278748663,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T08:32:28.663Z"},{"id":1777282443550,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T09:34:03.550Z"},{"id":1777282452430,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T09:34:12.430Z"},{"id":1777287698014,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T11:01:38.014Z"},{"id":1777287699310,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T11:01:39.310Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240080 | ACT-019 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Discuss mechanism for the Cap purchase between new plant and Signet | Manish Manjhi | Manish Manjhi | 2026-04-28 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""" | Mr. Saurabh Signet Work | [{"id":1777278758536,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T08:32:38.536Z"},{"id":1777278759740,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T08:32:39.740Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240081 | ACT-020 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Show Mr. Saurabh, the clamps issue | Manish Manjhi | Manish Manjhi | 2026-04-27 | COMPLETED | Done | NORMAL | 0 | [] | 2026-04-25 | """"""""" | Mr. Saurabh Signet Work | [{"id":1777278763324,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T08:32:43.324Z"},{"id":1777278764423,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T08:32:44.423Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240082 | ACT-021 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Purchase stud clamp for the PE moulding area | Manish Manjhi | Manish Manjhi | 2026-04-27 | IN PROCESS | Sent to Himanshu for purchase | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240083 | ACT-022 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Discuss with Mr. Parash for soft PVC moulding material 50 Kg use in the chair | Manish Manjhi | Manish Manjhi | 2026-04-27 | COMPLETED | Spoken with Mr. Parash, today they are exploring it. Tomorrow he will confirm | NORMAL | 0 | [] | 2026-04-25 | 2026-05-01 | Mr. Saurabh Signet Work | [{"id":1777620665746,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-05-01T07:31:05.746Z"},{"id":1777620667686,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-05-01T07:31:07.686Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240084 | ACT-023 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Get a new punch for the bend 110x87.5 or take it from old chinese collapsible mould | Manish Manjhi | Manish Manjhi | 2026-04-27 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240085 | ACT-024 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Take written action for the take-up and joiner issue and send it to the vendor if satisfies | Manish Manjhi | Manish Manjhi | 2026-04-27 | IN PROCESS | Mail shared with Mr. Pandey to confirm, will share it tonight during his Roster time | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240086 | ACT-025 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | PP material we found use it by adding 30% CPN and use it on non welding material - Bobbin, elbow, tee | Manish Manjhi | Manish Manjhi | 2026-04-27 | IN PROCESS | "" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777356144424,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Started from last one week. Will take 4 to 5 months","ts":"2026-04-28T06:02:24.424Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240087 | ACT-026 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Add PVC S350 machine for servo work | Manish Manjhi | Manish Manjhi | 2026-04-27 | IN PROCESS | On 27th Devanshi team visited and we have communicated the same to them, they will share the quotation by Wednesday | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240088 | ACT-027 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Install locating plate on the fast moving mould. | Manish Manjhi | Manish Manjhi | 2026-05-02 | IN PROCESS | 1. Getting Thapa for locating ring stand development. 2. Parallely all the locating ring will be segregated by Wednesday. 3. Once ring is identified where it is absent they will put it and as & when a mould is taken out it will go for tapping and drilling to fix it | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240089 | ACT-028 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Define the MTS for PVC and PE and ensure 45 days once mould is start. | Manish Manjhi | Manish Manjhi | 2026-04-29 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240090 | ACT-029 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Bring Jena and Gyaneshwar for SP 550 and discuss the mech issue. | Manish Manjhi | Manish Manjhi | 2026-04-28 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777271383148,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish has marked this action as complete and sent it for confirmation by Manish.","ts":"2026-04-27T06:29:43.148Z"}] | TRUE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240091 | ACT-030 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Share a daily report with Mr. Saurabh on RM consumption and yield losses. | Manish Manjhi | Manish Manjhi | 2026-04-29 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240092 | ACT-031 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-25 | Fix one machine for POM material and use RP and Grinder parallely. | Manish Manjhi | Manish Manjhi | 2026-04-28 | IN PROCESS | TD 275 II is fixed for POM | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240093 | ACT-032 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Compressor of Injection Moulding has to be installed | Manish Manjhi | Manish Manjhi | 2026-04-08 | IN PROCESS | Vendor came on Tuesday (7th). Work in progress, as per Mr. Tiwari, today pressure will be developed and tomorrow they will check if there is any leakage, if everything goes well, on 9th they will start it. | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289543103,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Vendor came on Tuesday (7th). Work in progress, as per Mr. Tiwari, today pressure will be developed and tomorrow they will check if there is any leakage, if everything goes well, on 9th they will start it. Leakage observed on 9th Apr, again today (10th Apr) vendor will check after rectification. 13 Apr: Compressor is getting heated","ts":"2026-04-27T11:32:23.103Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240094 | ACT-033 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Get the closure of the compressor VFD plan across the plants, and also we have to implement it within 7 days (check pressure transducer idea of Mr. Pandey) | Manish Manjhi | Manish Manjhi | 2026-05-02 | IN PROCESS | """"" | """"" | 2 | [{"date":"2026-04-27","from":"\"","to":"2026-05-09","by":"Manish Manjhi"},{"date":"2026-04-27","from":"2026-05-09","to":"2026-05-02","by":"Manish Manjhi"}] | " | """"" | """"" | [{"id":1777289215223,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Dewas:\n1. Air Compressor - GA 160 and GA45\n2. Motors on hammers 50HP (2 Nos) and 120 HP (1 Nos)\n3. APFC Panel \n4. Cooling tower controller to stopand start fan as per temperature required\n5. Requested hammers and IBH motor reading and current to check any abnormality\n\nAdroit:\n1. Broach machine (6 Nos - 50 HP Motor) - Install drive and idle logic to stop the machine.\n2. Air Compressor - VFD\n3. Requested Induction and Paint Booth conveyor motor reading and current to check any abnormality\n\nTomorrow I will share a detail charter for the same with projected cost and saving ROI, so that you can provide approval accordingly","ts":"2026-04-27T11:26:55.223Z"},{"id":1777289268530,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Test","ts":"2026-04-27T11:27:48.530Z"},{"id":1777289271149,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Test","ts":"2026-04-27T11:27:51.149Z"},{"id":1777289277202,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Test\ntEST 2","ts":"2026-04-27T11:27:57.202Z"},{"id":1777289401156,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Adroit:\n1. Broach machine (6 Nos - 50 HP Motor) - Install drive and idle logic to stop the machine.\n2. Air Compressor - VFD\n3. Requested Induction and Paint Booth conveyor motor reading and current to check any abnormality\n\nTomorrow I will share a detail charter for the same with projected cost and saving ROI, so that you can provide approval accordingly","ts":"2026-04-27T11:30:01.157Z"}] | " | """"" | """"" | """"" | """"" | """"" | """""
1777128240095 | ACT-034 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Get the fixture ready to ensure fitment is control | Manish Manjhi | Manish Manjhi | 2026-05-09 | IN PROCESS | Develop it | NORMAL | 1 | [{"date":"2026-04-27","from":"2026-04-10","to":"2026-05-09","by":"Manish Manjhi"}] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289601860,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Mr. Saurabh, gave permission to develop it on 25th Apr","ts":"2026-04-27T11:33:21.860Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240096 | ACT-035 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Check with Mr. Tiwari and Mr. Himanshu on the Servo Work (NP 100 I) | Manish Manjhi | Manish Manjhi | 2026-04-06 | IN PROCESS | Delivery got delayed, it will be dispatched today and by 8th we will get the status from the vendor. | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289669842,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Delivery got delayed, it will be dispatched today and by 8th we will get the status from the vendor. @8th: Vendor found the issue, but he tomorrow's time to suggest possible solution","ts":"2026-04-27T11:34:29.842Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240097 | ACT-036 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | For each Machine create a shadow wall or tool box to keep the machine relevant tools | Manish Manjhi | Manish Manjhi | 2026-05-09 | IN PROCESS | Will share by 9th Apr. | NORMAL | 1 | [{"date":"2026-04-27","from":"2026-04-02","to":"2026-05-09","by":"Manish Manjhi"}] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289694872,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Will share by 9th Apr. We have locating plate define for mould and maintain it","ts":"2026-04-27T11:34:54.872Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240098 | ACT-037 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Get the team for mechanical maintenance of SP550 and ensure we also want to test of the material which they suggest to install | Manish Manjhi | Manish Manjhi | 2026-04-06 | IN PROCESS | We spoke that despite Servo work, we have to do few mechnical work. For the same Mr. Hemant has shared the details with two of his vendors. They will share the details by 9th Apr. | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289724224,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"We spoke that despite Servo work, we have to do few mechnical work. For the same Mr. Hemant has shared the details with two of his vendors. They will share the details by 9th Apr. Bush casting discuss with Mr. Gora and we have earlier done it","ts":"2026-04-27T11:35:24.224Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240099 | ACT-038 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Confirm whether we are getting D2 material for the grider blade or not with Mr. Pandey and Mr. Himanshu (CPVC) | Manish Manjhi | Manish Manjhi | 2026-04-06 | IN PROCESS | Indent has been raised for the same, Order will be placed tomorrow (4th), it will take 20 to 25 days. | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289742432,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"Indent has been raised for the same, Order will be placed tomorrow (4th), it will take 20 to 25 days.","ts":"2026-04-27T11:35:42.432Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240100 | ACT-039 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Check the availability of runner clipper to ease the operator time and effort in runner cutting | Manish Manjhi | Manish Manjhi | 2026-04-04 | IN PROCESS | Not all machine have, they have lost few. With shadow wall and regular review via linewalk it will be controlled. | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240101 | ACT-040 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Discuss with Mr. Himanshu for grinder payment issue (Rotor) - PE Moulding Big Grinder | Manish Manjhi | Manish Manjhi | 2026-04-06 | COMPLETED | Amit went to validate the work completion and found some threading work was still pending, hence vendor is completing it today and tomorrow we will get it. | NORMAL | 0 | [] | 2026-04-25 | 2026-04-27 | Mr. Saurabh Signet Work | [{"id":1777289764969,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by Manish Manjhi.","ts":"2026-04-27T11:36:04.969Z"},{"id":1777289766206,"author":"System","authorInitials":"SYS","authorColor":"#1E8449","text":"Manish Manjhi has confirmed completion. Action is now COMPLETED.","ts":"2026-04-27T11:36:06.206Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240102 | ACT-041 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Install temporary green net or permanent sheets for the partition between the CPVC and Moulding plant | Manish Manjhi | Manish Manjhi | 2026-04-30 | IN PROCESS | The fabrication team is already engaged for fire related work for next 10 to 15 days. Hence we are seeking contractor for the same. Material today approved by Mukesh Sir and Tiwari Ji is planning to get this work done from Mr. Mandal (he is currently making pvc pipe bins along the boundary). | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [{"id":1777289779825,"author":"Manish Manjhi","authorInitials":"MM","authorColor":"#272262","text":"The fabrication team is already engaged for fire related work for next 10 to 15 days. Hence we are seeking contractor for the same. Material today approved by Mukesh Sir and Tiwari Ji is planning to get this work done from Mr. Mandal (he is currently making pvc pipe bins along the boundary). From monday work will start (13th Apr)","ts":"2026-04-27T11:36:19.825Z"}] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240103 | ACT-042 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | Photo Sensor - Discuss with the vendor for further rate negotiation | Manish Manjhi | Manish Manjhi | 2026-04-28 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1777128240104 | ACT-043 | Mr. Saurabh Review Meeting | General | Signet | 2026-04-02 | List of old items for Saurabh Shaktiman (old dump lot) in PVC area and identify material for grinding | Manish Manjhi | Manish Manjhi | 2026-04-28 | IN PROCESS | """""""" | NORMAL | 0 | [] | 2026-04-25 | """"""""""""""""" | Mr. Saurabh Signet Work | [] | FALSE | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """"""""""""""""" | """""""""""""""""
1778108322577 | ACT-027 | Mr. Saurabh Review Meeting | General | Signet | 2026-05-06 | Test action point for bug hunting. | Prashant | Manish | 2026-05-10 | IN PROCESS |  | NORMAL | 0 | [] | 2026-05-06 |  | Mr. Saurabh Signet Work | [] | FALSE

## Meetings
id | type | plant | time | dur | facilitator | recurring | project | completedSessions | "
M1777123190276 | Mr. Saurabh Review Meeting | Signet | 7:00 | 60 | Manish | TRUE | Mr. Saurabh Signet Work | [] | "

## Projects
id | name | plant | owner | start | end | status | priority | objective | scope | budget | sponsor | team | milestones | risks
PR1777123102460 | Mr. Saurabh Signet Work | Signet | Manish Manjhi | 2026-04-25 | 2026-08-31 | NOT STARTED | CRITICAL | " | " | " | Manish Manjhi | [] | [] | "