## Machines
id | name | plant | dept | type | assetNo
MC01 | ALL | Signet | PE | Manual | M/c-1
MCO1 | ALL | Adroit | ALL | Hybrid | M/c-1

## Users
id | name | username | password | role | plant | dept | superior | phone | email | initials
U01 | Prashant Singh | Prash | 1401 | MD | Signet | PE | CMD | 7049091928 | singhprashant7972@gmail.com | PS
U02 | Manish Manjhi | Manish | 1975 | HOD | Signet | ALL | MD | " | manish.manjhi@groupsignet.com | MM
U03 | Aarti Hr | Aarti@Adroit | 145236789 | HOD | Both | General | """""""""""""""""""""""""""""""""""""""""""""""""""""""""""" | 0 | Hr@Adroit.Com | AH
U04 | Mohit Patsariya | mohit_pmo | 8839738487 | Supervisor | Adroit | Overall | Manish Manjhi | 8839738487 | mohit.patsariya@adroitindustries.com | MP

## Plants
id | name | location | head
P1 | Signet | Pithampur | Saurabh Sangla
P2 | Adroit | Pithampur | Saurabh Sangla
P3` | Both | Indore | Mukesh Sangla

## Departments
id | name | plant | head | icon
D1 | PE | Signet | Saurabh Sangla | 🔹
D2 | PVC | Signet | Saurabh Sangla | 🔹
D3 | General | Both | Saurabh Sangla | 🔹
D4 | Overall | Adroit | Saurabh Sangla | """

## Actions
id | sn | text | responsible | due | status | priority | section | source | plant | dept | machine | reason | remarks | dateOfAction | created | closedOn | closedBy | revisions | revisionHistory | messages | pendingConfirmation | allocatedBy | project | src | reasonOfAction | machineName | actionPointType
1781503466825 | ACT-001 | Testing | Prashant Singh | 2026-06-14 | IN PROCESS | NORMAL | General | """""""""""""""" | Signet | """""""""""""""" | """""""""""""""" | """""""""""""""" | Test | 2026-06-15 | 2026-06-15 | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Testing | Quick Add | """"""""""""""" | ALL | Improvement
1781522231331 | ACT-002 | TESTING2 | Prashant Singh | 2026-06-15 | IN PROCESS | NORMAL | PE | """"""""""""""" | Signet | """"""""""""""" | """"""""""""""" | """"""""""""""" | """"""""""""""" | 2026-06-15 | 2026-06-15 | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | Quick Add | """"""""""""""" | ALL | Preventive Action
1777128240079 | ACT-018 | Tank Cap trail to be done | Manish Manjhi | 2026-04-28 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Done | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240080 | ACT-019 | Discuss mechanism for the Cap purchase between new plant and Signet | Manish Manjhi | 2026-04-28 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | 2026-06-01 | Manish | 0 | [] | [] | FALSE | Manish Manjhi | Mr. Saurabh Signet Work | """"""""""""""" | Test | ALL | Preventive Action
1777128240081 | ACT-020 | Show Mr. Saurabh, the clamps issue | Manish Manjhi | 2026-04-27 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Done | 2026-04-25 | """"""""""""""" | 2026-06-02 | Manish | 0 | [] | [] | FALSE | Manish Manjhi | Mr. Saurabh Signet Work | """"""""""""""" | Test | ALL | Preventive Action
1777128240082 | ACT-021 | Purchase stud clamp for the PE moulding area | Manish Manjhi | 2026-05-08 | NOT STARTED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Sent to Himanshu for purchase | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Manish Manjhi | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240083 | ACT-022 | Discuss with Mr. Parash for soft PVC moulding material 50 Kg use in the chair | Manish Manjhi | 2026-04-27 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Spoken with Mr. Parash, today they are exploring it. Tomorrow he will confirm | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Manish Manjhi | Mr. Saurabh Signet Work | """"""""""""""" | Preventive Action | ALL | Preventive Action
1777128240084 | ACT-023 | Get a new punch for the bend 110x87.5 or take it from old chinese collapsible mould | Manish Manjhi | 2026-04-27 | IN PROCESS | NORMAL | Business Excellence | Mr. Saurabh Review Meeting | Signet | Business Excellence | """"""""""""""" | ALL | """"""""""""""""""""""" | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Manish Manjhi | Mr. Saurabh Signet Work | """"""""""""""" | Corrective Action | ALL | Preventive Action
1777128240085 | ACT-024 | Take written action for the take-up and joiner issue and send it to the vendor if satisfies | Manish Manjhi | 2026-04-27 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Mail shared with Mr. Pandey to confirm, will share it tonight during his Roster time | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240086 | ACT-025 | PP material we found use it by adding 30% CPN and use it on non welding material - Bobbin, elbow, tee | Manish Manjhi | 2026-04-27 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | Ongoing in the practice | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240087 | ACT-026 | Add PVC S350 machine for servo work | Manish Manjhi | 2026-04-27 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | On 27th Devanshi team visited and we have communicated the same to them, they will share the quotation by Wednesday | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240088 | ACT-027 | Install locating plate on the fast moving mould. | Manish Manjhi | 2026-05-02 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | 1. Getting Thapa for locating ring stand development. 2. Parallely all the locating ring will be segregated by Wednesday. 3. Once ring is identified where it is absent they will put it and as & when a mould is taken out it will go for tapping and drilling to fix it | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240089 | ACT-028 | Define the MTS for PVC and PE and ensure 45 days once mould is start. | Manish Manjhi | 2026-04-29 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | 2026-05-10 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240090 | ACT-029 | Bring Jena and Gyaneshwar for SP 550 and discuss the mech issue. | Manish Manjhi | 2026-04-28 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240091 | ACT-030 | Share a daily report with Mr. Saurabh on RM consumption and yield losses. | Manish Manjhi | 2026-04-29 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | """"""""""""""" | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240092 | ACT-031 | Fix one machine for POM material and use RP and Grinder parallely. | Manish Manjhi | 2026-04-28 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | TD 275 II is fixed for POM | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | """"""""""""""" | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240093 | ACT-032 | Compressor of Injection Moulding has to be installed | Manish Manjhi | 2026-04-08 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Vendor came on Tuesday (7th). Work in progress, as per Mr. Tiwari, today pressure will be developed and tomorrow they will check if there is any leakage, if everything goes well, on 9th they will start it. | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240094 | ACT-033 | Get the closure of the compressor VFD plan across the plants, and also we have to implement it within 7 days (check pressure transducer idea of Mr. Pandey) | Manish Manjhi | 2026-05-02 | IN PROCESS | """""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""""" | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | """"""""""""""" | " | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | Corrective Action | ALL | Preventive Action
1777128240095 | ACT-034 | Get the fixture ready to ensure fitment is control | Manish Manjhi | 2026-05-09 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Develop it | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240096 | ACT-035 | Check with Mr. Tiwari and Mr. Himanshu on the Servo Work (NP 100 I) | Manish Manjhi | 2026-04-06 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Delivery got delayed, it will be dispatched today and by 8th we will get the status from the vendor. | 2026-04-25 | """"""""""""""" | 2026-06-01 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240097 | ACT-036 | For each Machine create a shadow wall or tool box to keep the machine relevant tools | Manish Manjhi | 2026-05-09 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Will share by 9th Apr. | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240098 | ACT-037 | Get the team for mechanical maintenance of SP550 and ensure we also want to test of the material which they suggest to install | Manish Manjhi | 2026-04-06 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | We spoke that despite Servo work, we have to do few mechnical work. For the same Mr. Hemant has shared the details with two of his vendors. They will share the details by 9th Apr. | 2026-04-25 | """"""""""""""" | 2026-06-01 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240099 | ACT-038 | Confirm whether we are getting D2 material for the grider blade or not with Mr. Pandey and Mr. Himanshu (CPVC) | Manish Manjhi | 2026-04-06 | NOT STARTED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Indent has been raised for the same, Order will be placed tomorrow (4th), it will take 20 to 25 days. | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240100 | ACT-039 | Check the availability of runner clipper to ease the operator time and effort in runner cutting | Manish Manjhi | 2026-04-04 | DROPPED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Not all machine have, they have lost few. With shadow wall and regular review via linewalk it will be controlled. | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240101 | ACT-040 | Discuss with Mr. Himanshu for grinder payment issue (Rotor) - PE Moulding Big Grinder | Manish Manjhi | 2026-04-06 | COMPLETED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | Amit went to validate the work completion and found some threading work was still pending, hence vendor is completing it today and tomorrow we will get it. | 2026-04-25 | """"""""""""""" | 2026-06-01 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240102 | ACT-041 | Install temporary green net or permanent sheets for the partition between the CPVC and Moulding plant | Manish Manjhi | 2026-04-30 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | The fabrication team is already engaged for fire related work for next 10 to 15 days. Hence we are seeking contractor for the same. Material today approved by Mukesh Sir and Tiwari Ji is planning to get this work done from Mr. Mandal (he is currently making pvc pipe bins along the boundary). | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | Corrective Action | ALL | Preventive Action
1777128240103 | ACT-042 | Photo Sensor - Discuss with the vendor for further rate negotiation | Manish Manjhi | 2026-04-28 | DROPPED | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1777128240104 | ACT-043 | List of old items for Saurabh Shaktiman (old dump lot) in PVC area and identify material for grinding | Manish Manjhi | 2026-04-28 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | """"""""""""""" | 2026-04-25 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1778108322577 | ACT-027 | Test action point for bug hunting. | Prashant | 2026-05-10 | IN PROCESS | NORMAL | General | Mr. Saurabh Review Meeting | Signet | General | ALL | ALL | """"""""""""""" | 2026-05-06 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1778237015324 | ACT-028 | Testing 1` | Prashant | 2026-05-10 | IN PROCESS | CRITICAL | General | Quick Add | Signet | General | ALL | ALL | """"""""""""""" | 2026-05-08 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | Compliance / audit finding | ALL | Preventive Action
1778490244889 | ACT-029 | testing | Manish Manjhi | 2026-05-20 | IN PROCESS | NORMAL | General | Quick Add | Signet | General | ALL | ALL | """"""""""""""" | 2026-05-11 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1778508756133 | ACT-030 | fsdfdsfsdf | Prashant | 2026-05-21 | COMPLETED | NORMAL | General | Quick Add | Signet | General | ALL | ALL | sdfdsfsdfs | 2026-05-11 | """"""""""""""" | 2026-05-11 | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | sddssds | ALL | Preventive Action
1779824430871 | ACT-031 | Testing | Prashant | 2026-05-28 | IN PROCESS | NORMAL | PE | Quick Add | Signet | PE | ALL | ALL | Testing | 2026-05-26 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1780379533132 | ACT-032 | Testing | Prashant | 2026-06-20 | IN PROCESS | NORMAL | PE | Quick Add | Signet | PE | ALL | ALL | Hello | 2026-06-02 | """"""""""""""" | """"""""""""""" | Manish | 0 | [] | [] | FALSE | Prashant | Mr. Saurabh Signet Work | """"""""""""""" | """"""""""""""" | ALL | Preventive Action
1780380063722 | ACT-033 | Escalation Testing | Manish Manjhi | 2026-06-10 | PENDING CONFIRM | WARNING | General | Quick Add | Signet | General | ALL | ALL | Test Remark | " | """""""""""""" | """""""""""""" | """""""""""""" | " | """""""""""""" | [{"id":1781680538616,"author":"System","authorInitials":"SYS","authorColor":"#272262","text":"Manish Manjhi has marked this action as complete and sent it for confirmation by .","ts":"2026-06-17T07:15:38.616Z"}] | TRUE | """""""""""""" | """""""""""""" | """""""""""""" | """""""""""""" | """""""""""""" | """"""""""""""

## Meetings
id | type | plant | date | status | attendees | duration | actionCount | notes | name | time | dur | facilitator | recurring | recurrence | project | completedSessions
M1780483326652 | testing | All | " | " | ["\""] | " | " | " | testing | 10:00 | 60 | Prashant Singh | FALSE | daily | Testing | []

## Projects
id | name | plant | dept | status | owner | startDate | endDate | progress | description | start | end | priority | objective | scope | budget | sponsor | milestones | risks | team
PR1780483280105 | Testing | Signet | """"""""""""""" | NOT STARTED | Admin | """"""""""""""" | """"""""""""""" | """"""""""""""" | """"""""""""""" | 2026-06-30 | 2026-07-30 | NORMAL | Testing Purpose | Testing | 0 | Admin | [{"name":"New Milestone","due":"2026-06-20","done":false}] | """"""""""""""" | []

## EscalationMatrix
id | level | label | overdueDays | overdueHrs | target | notifyMethod | priorities | applicableTo | color | active | description
E6a0d7784 | 1 | Level 1 — New Tier | 1 | 24 | Supervisor | In-App + Email | ["CRITICAL"] | All | #7F8C8D | TRUE | """""""""""""""""""""""""""""""""""""""
Eae621c7f | 2 | Level 2 — New Tier | 1 | 24 | Shift Engineer | In-App + Email | ["CRITICAL"] | All | #7F8C8D | TRUE | """""""""""""""""""""""""""""""""""""""

## MeetingPresets
type | attendees | instructions

## Reasons
id | text | category | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R001 | Machine breakdown / failure | Equipment | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R002 | Quality defect observed | Quality | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R003 | Safety hazard identified | Safety | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R004 | Process deviation found | Process | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R005 | Customer complaint follow-up | Customer | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R006 | Preventive maintenance due | Maintenance | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R007 | Material shortage / delay | Supply Chain | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R008 | Operator error / training gap | People | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R009 | Tool / die wear or damage | Equipment | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R010 | Energy / utility issue | Utilities | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R011 | Compliance / audit finding | Compliance | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R012 | Yield loss / rework identified | Quality | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R013 | New project / improvement initiative | Projects | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R014 | Management directive | Management | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""
R015 | Repeat issue — root cause pending | Quality | " | "" | """ | """" | """"" | """""" | """"""" | """""""" | """"""""" | """""""""" | """"""""""" | """""""""""" | """"""""""""" | """""""""""""" | """""""""""""""

## Audit
id | ts | sn | text | level | target | reason
1.7815e+12 | 2026-06-15T06:04:28.370Z | ACT-001 | Testing | 1 | Supervisor | 30h overdue — Level 1 — Supervisor Alert
1.7815e+12 | 2026-06-15T10:59:32.689Z | ACT-002 | testinng2 | 3 | Plant Head | 130h overdue — Level 3 — Plant Head Review
1.7815e+12 | 2026-06-15T11:17:12.855Z | ACT-002 | TESTING2 | 1 | Supervisor | 11h overdue — Level 1 — Supervisor Alert
1.7815e+12 | 2026-06-15T12:24:26.420Z | ACT-021 | Purchase stud clamp for the PE moulding area | 1 | Supervisor | 924h overdue — Level 1 — Supervisor Alert
1.7815e+12 | 2026-06-15T12:24:26.420Z | ACT-022 | Discuss with Mr. Parash for soft PVC moulding material 50 Kg use in the chair | 1 | Supervisor | 1188h overdue — Level 1 — Supervisor Alert
1.7815e+12 | 2026-06-15T12:24:26.420Z | ACT-023 | Get a new punch for the bend 110x87.5 or take it from old chinese collapsible mould | 1 | Supervisor | 1188h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-024 | Take written action for the take-up and joiner issue and send it to the vendor if satisfies | 1 | Supervisor | 1212h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-025 | PP material we found use it by adding 30% CPN and use it on non welding material - Bobbin, elbow, tee | 1 | Supervisor | 1212h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-026 | Add PVC S350 machine for servo work | 1 | Supervisor | 1212h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-027 | Install locating plate on the fast moving mould. | 1 | Supervisor | 1092h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-028 | Define the MTS for PVC and PE and ensure 45 days once mould is start. | 1 | Supervisor | 1164h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-029 | Bring Jena and Gyaneshwar for SP 550 and discuss the mech issue. | 1 | Supervisor | 1188h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-030 | Share a daily report with Mr. Saurabh on RM consumption and yield losses. | 1 | Supervisor | 1164h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-031 | Fix one machine for POM material and use RP and Grinder parallely. | 1 | Supervisor | 1188h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-032 | Compressor of Injection Moulding has to be installed | 1 | Supervisor | 1668h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-034 | Get the fixture ready to ensure fitment is control | 1 | Supervisor | 924h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-036 | For each Machine create a shadow wall or tool box to keep the machine relevant tools | 1 | Supervisor | 924h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-038 | Confirm whether we are getting D2 material for the grider blade or not with Mr. Pandey and Mr. Himanshu (CPVC) | 1 | Supervisor | 1716h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-041 | Install temporary green net or permanent sheets for the partition between the CPVC and Moulding plant | 1 | Supervisor | 1140h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-043 | List of old items for Saurabh Shaktiman (old dump lot) in PVC area and identify material for grinding | 1 | Supervisor | 1188h overdue — Level 1 — Supervisor Alert
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-028 | Testing 1` | 4 | MD | 900h overdue — Level 4 — MD Intervention
1.7817e+12 | 2026-06-17T07:09:28.751Z | ACT-033 | Escalation Testing | 3 | Plant Head | 156h overdue — Level 3 — Plant Head Review